## What is new in V2
What is New in Version 2
Summary of Key Changes
Following the release of version one (V1) there have been important updates from the WA state government. Version 2 has been updated to reflect these changes. All changes can be found throughout the document including in the resources and stages tabs, and are indicated by (new) or (updated):
(New) | Indicates that either the sub operation title is new or there is a new resource attached to an exisiting title. Please check on the example and well as the resource for context
(updated) | Indicates that there has been an update for either the example given to match current guidelines, or an updated resource inline with current guidelines
The below list is a summary of the key changes represented in this plan. If you have an exisiting plan these are the key updates to take note of to efficiently update your current plan.
Removal of RACGP resource - Responding to a COVID positive case in the practice team.
This was removed by the RACGP and has been replaced by references to the WA state health transistional policies ( see below)
Addition of WA State Health Department - Transitional Policies.
These transitional policies are the directions for healthworker furlough, testing, SAR guidelines and PPE among others and have been encorporated in resources and examples
Addition of COVID Care at home program resources.
The examples and resources have been adjusted to take in to account the important update of the COVID Care at home program
Addition of WA State definition resources for close contacts, testing and isolation, critical workers, high and very high case loads.
These have been encorporated in examples and connected resources
Healthpathways COVID -19 pathways
These are consisitantly being updated to support clinicians and mangement. Encorporating transitional policies, COVID care at home,and new state definitions
NEW - Glossary tab.
For acronyms and helpful terms, all connected to the helpful resources tab. There is additional space for the practice to add their own acronyms and terms if desired.
Increased customisation options
Version 2 has been modified to allow users to add rows in to the stages, modify cells and add in hyperlinks.
The resource section is larger. Practices can now add in additional resources with hyperlinks to any blank spaces and create their own custom library.
To prevent the tools hyperlinks and sructure from breaking, the structure and some content is locked and cannot be modified. Please call PracticeAssist if you discover any issues with the tool
How to make updates to your current plan? It is individual preference, there is no right or wrong, here are some examples of what can be done:
Copy sections from your V1 in to V2 - we have kept all the original titles the same, and where there are amendments this will fit your data
Check the updates in V2 or simply review the key changes above and amend your V1 accordingly.
Please note that due to the locking function of the V1 spreadsheet hyperlinks cannot be created. This can now be done in V2
Disclaimer WA Primary Health Alliance’s publications and the material within them are intended for use by health professionals for general information purposes and do not replace clinical decision making. Please read our full disclaimer. While the Australian Government contributed funding for this material, it has not reviewed the content and is not responsible for any injury, loss or damage however arising from the use of or reliance on the information provided herein.

## How to use this spreadsheet
Practice Assist
Planned Pandemic Response Tool (PPRT)
Version 2 - March 2022
How to use this spreadsheet:
Tip - For practices using the Version 1 PPRT. Please refer to the first tab "what is new in V2" for a summary of changes to be incorporated in to your existing plan. |  |  |  | Or click here to go direct to the tab
Tip - This document has been created with hyperlinks. To access the full potential of this document download it and use with a computer/ device connected to the internet.
NEW - Glossary tab. | For acronyms and helpful terms, all connected to the helpful resources tab. There is additional space for the practice to add their own acronyms and terms if desired.
1. This planning tool is designed to help create a Pandemic Response Plan . It is a place to write down the specific changes to the practices day to day operations at each stage of a pandemics progression. This plan is specific to the practice. Each part is customisable for the practice including escalations, triggers and responses for each stage .With each section there is a suggestions, guidance and resources. Edit as appropriate for your team . Your practice can go up and down the escalations to respond to public health directions.
2. This tool has FOUR suggested stages of escalation . At each stage you can define how the practice operations change to suit the escalation. The tool can closely match the level of "System Alert and Response (SAR)" see glossary.
| Escalation - Stage one : | Definition: Low Risk/High Vigilance. Position of readiness and a low potential of cases
| Escalation - Stage two: | Definition: High Risk/ High Vigilance. COVID -19 present in your local community, all patients a potential risk of infection
| Escalation - Stage three: | Definition :Living with COVID-19. Widespread transmission - establishing a new normal of practice
| Escalation - Practice Closure: | Definition: Practice closure - No PPE available/ Catastrophic HR deficit due to sickness or isolation / Public Health Closure
3. Define your practice escalation triggers. The first task with each escalation stage is to define what is the specific trigger that will cause the practice to move in to this new mode of operation. This is customisable, recognising that this trigger will differ depending on location and exposure of the practice. There is an example of what a trigger can be for each stage. It is important to apply SMART to the practice's trigger so that there is no doubt when the plan should be enacted.
4. Practice operations column: Each stage is divided in to key areas of practice operations . Under each key practice operation are sub operations. Both the practice operations and the sub operations can be added too or omitted.
5. Adaptions to operations column. This section is where it is detailed what adaptions the practice will make to that specific operation during a particular stage. There is an AIM suggested at the top of each section to summarise the overall operational change. The tool gives suggested changes that the practice could make. This section is best to be completed after reading the complementary Practice Assist resources and linked sites. Be SMART with the practice adaptions, and hyperlink or reference to any protocols created for the new operation if you choose. Additional rows and hyperlinks can be added to customise to the practices requirements.
6. Resources. This tab has a collection of all of the resources suggested in this document to assist with formulating the practice specific response. Each escalation stage has hyperlinks to a key resource (s) listed in this tab. There is space for further resources to be added by the practice to create a bespoke practice library.
7. Review the plan. Once created this plan is designed to be dynamic and adapt with changes. TRIAL IT with your team
There are multiple PDSA's that can be created for this plan. |  |  | Check our QI Tool Kit and speak with your QI coach for further assistance
Hints and tips
There may be times where the adaptation to the practice operations is the same at every stage. I.e. your communication responsible persons are likely to be the same throughout. If this is the case save additional typing by either using a "copy and paste" function, a hyperlink function or use a spreadsheet function to reference one cell with the information for each stage. Alternatively simply write - "as per stage one"
More information and feedback :
Please contact Practice Assist 1800 2 ASSIST (277478) or email practiceassist@wapha.org.au
Acknowledgments
We would like to acknowledge the Tasmanian PHN COVID-19 Pandemic Toolkit (2020) in the contribution to this document
Disclaimer WA Primary Health Alliance’s publications and the material within them are intended for use by health professionals for general information purposes and do not replace clinical decision making. Please read our full disclaimer. While the Australian Government contributed funding for this material, it has not reviewed the content and is not responsible for any injury, loss or damage however arising from the use of or reliance on the information provided herein.

## Stage 1 Low Risk
Pandemic Response Plan Stage 1 - Low Risk, High Vigilance
This stage is designed to account for both the increased possibility of an unrecognised COVID-19 positive case entering a general practice and an increase in WA state restrictions. This is a face-to-face model except for those with clinical symptoms and/or epidemiology (e.g. patient history of recent travel, contact with hotspots).
Consider what would be a trigger for your practice to implement this Stage 1? Plan and write it in the blank space below - select the space below to see an example.
(Consider using SMART (Specific, Measurable, Achievable, Realistic, and Timely) to define)
Click in this box for suggestions
Practice Operations | Adaptions to Operations for Stage 1
You can add or remove these operations depending on the relevancy to your practice. Please click on each sub -operation to be taken to the appropriate resource or group of resources. | What operations will your practice change to adapt? Try to be explicit. Some items may require a separate procedure document to detail the changes. Select the cells on the right with "Ex." for an example.
Patient Journey/Flow Changes
Aim: Introduce proactive screening in accordance to state health guidelines, create robust triage actions for patients with epidemiology and / or symptoms
Screening of patients |  | Ex.
Greeting and screening questions |  | Ex.
Entrance/Front Desk |  | Ex.
PPE use for patients and greeting staff (updated) |  | Ex.
Non-patient Traffic
Aim: To reduce patient and people traffic in your practice that is not essential.
Support persons |  | Ex.
Contractors ( maintenance) |  | Ex.
Pathology collection |  | Ex.
Pharmacy pick up of prescriptions etc. |  | Ex.
All other non-patient visitors |  | Ex.
Triaging
Aim: To adapt your practice's triaging process based on the latest clinical and testing advice. Consider the use of Telehealth, isolation room, PPE.
Adapt triage process to match current advice and practice position, consider: |  | Ex.
Triage resources for staff (updated) |  | Ex.
Triage of patients with cold/flu symptoms |  | Ex.
Triage of complex patients: Young children, the elderly, pregnant people, those difficult to assess via telehealth or those with difficulty in communication (updated) |  | Ex.
Handling patients that have physically arrived with epidemiology or symptoms (updated) |  | Ex.
What services are available in our region, including testing, after hours (new) |  | Ex.
Definitions for staff ( close contact, confirmed case) (updated) |  | Ex.
Triaging for COVID Positive patients (new) |  | Ex.
Personal Protective Equipment (PPE)
Aim: Have adequate PPE stores and know how and when it should be used for maximum efficiency.
Appropriate PPE usage dependent on risk (new) |  | Ex.
Stock |  | Ex.
Patient use and access (updated) |  | Ex.
Donning and Doffing (updated) |  | Ex.
Recording of fit test results |  | Ex.
Laundry and Uniform
Aim: Consider a creation of laundering guidelines, changing spaces, additional stock of uniform , use of scrubs ready for future escalation
Current uniform procedures (updated) |  | Ex.
At home laundering |  | Ex.
On-site laundering |  | Ex.
Practice layout changes /infection control
Aim: Make the inside of the practice as low risk for spread as reasonably possible and comply with social distancing regulations.
Seating distance and capacity (updated) |  | Ex.
Practice entrance and exit (updated) |  | Ex.
Isolation room entry and exit patient flow |  | Ex.
Waiting room |  | Ex.
Addition of doffing and donning areas |  | Ex.
Protection of staff , physical barriers, PPE |  | Ex.
Practice Cleaning |  | Ex.
Information to contract cleaners |  | Ex.
Clean air/ ventilation considerations (new) |  | Ex.
Isolation room/space utilisation
Aim: Create a designated isolation room/area to see vulnerable/difficult patients/children under a certain age.
Create a space/room/clinic time designated for seeing infectious patients or with current epidemiology |  | Ex.
Training on use of the isolation room and cleaning |  | Ex.
Cleaning schedules and responsibilities |  | Ex.
Isolation room/area - greeting, check in |  | Ex.
Isolation room/area - greeting, check out |  | Ex.
Telehealth
Aim: Enable or increase the use of Telehealth in your practice for greeting, treating and checking out patients remotely.
Enable Telehealth via phone/video call |  | Ex.
Use of Telehealth |  | Ex.
Non-Medicare covered patients (no Medicare card or not eligible for MBS items) |  | Ex.
E-prescribing and patient documentation
Aim: Enable methods to be able to remotely send prescriptions, pathology, referrals and patient documentation.
Patient documentation |  | Ex.
Prescriptions |  | Ex.
Messaging to other providers |  | Ex.
Utilise digital methods to send patient documentation |  | Ex.
Online booking and Website
Aim: Put processes in place to triage all patients booking on line for symptoms and epidemiology
Messaging and communication on your online platforms , and website |  | Ex.
Online booking preferences |  | Ex.
New software/systems |  | Ex.
Patient Communication
Aim: How are you going to communicate your changes effectively and enforce the changes
Hold music/message |  | Ex.
Receptionists' phone call script |  | Ex.
Communications and language (new) |  | Ex.
Communication and posters |  | Ex.
Effective Patient Communication ( updated) |  | Ex.
Practice social media |  | Ex.
Clinical Services
Aim: Reflect on all services provided, establish if any need to be restricted, modified or prioritised.
Aerosol Producing procedures |  | Ex.
Home/external visits (updated) |  | Ex.
Existing non-essential services (updated) |  | Ex.
COVID-19 Assessment and Management |  | Ex.
Home care COVID-19 patients via practice |  | Ex.
Adopting the COVID Care at Home Program (new) |  | Ex.
Aged Care / Hospital Visits (new) |  | Ex.
Administration/Non-clinical
Aim: Start planning and testing methods of working from home for the non-clinical aspects of the practice.
Daily, weekly and monthly list of duties and responsibility for the team |  | Ex.
Human Resources (HR)
Aim: Create a safe work environment and prepare your team for alternative working arrangements.
Working from home audit |  | Ex.
Working from home/external premises protocol |  | Ex.
Infection control training recent and up to date |  | Ex.
Staff training on PPE |  | Ex.
Management of an positive case in a team member - Create an outbreak management plan (new) |  | Ex.
Management of close contact in a team member - Create an outbreak management plan (new) |  | Ex.
Furlough advice for Healthcare workers (new) |  | Ex.
Management of a postive case within the workplace (new) |  | Ex.
IT and phones systems
Aim: To adapt existing IT and phone systems for remote work with minimal business disruptions.
IT |  | Ex.
Phone lines |  | Ex.
Software |  | Ex.
Communication and responsibilities
Aim: Assign responsibilities and accountabilities for enacting these stages changes and the communication to the whole team regarding changes and updates from the state
Role/s responsible for communicating the changes to the practice |  | Ex.
Role/s responsible for keeping abreast of changes in the COVID-19 pandemic |  | Ex.
Role/s responsible for agreeing to escalate or deescalate the stages |  | Ex.
GP Urgent Care Practices
Aim: Consider plans to keep services open for GP Urgent Care patients.
GP Urgent Care appointments |  | Ex.
Other
Aim: Use this space for anything else relevant to your practice that hasn't already been covered above.

## Stage 2 High Risk
Pandemic Response Plan Stage 2 - High Risk, High Vigilance
This stage is designed for a situation where COVID-19 is present within your local community where all patients/staff/visitors pose a potential risk of infection within the practice. Convert practice to a mainly virtual or other non-face-to-face model.
Consider what would be a trigger for your practice to implement this Stage 2? Plan and write it in the blank space below - select the space below to see an example.
(Consider using SMART (Specific, Measurable, Achievable, Realistic, and Timely) to define)
Click in this box for suggestions
Practice Operations | Adaptions to Operations for Stage 2
You can add or remove these operations depending on the relevancy to your practice. Please click on each operation to be taken to the appropriate resources. | What operations will your practice change to adapt further to the prior stage? Try to be explicit. Some items may require a separate procedure document to detail the changes. Select the cells on the right with "Ex." for an example.
Patient Journey/Flow Changes
Aim: To reduce the risk of infection in the practice by screening all patients prior to entering the building for epidemiology and symptoms. Increase non face to face models of care
Screening of patients |  | Ex.
Greeting and screening questions |  | Ex.
Entrance/Front Desk |  | Ex.
PPE use for patients and greeting staff (updated) |  | Ex.
Check in process |  | Ex.
Non-patient Traffic
Aim: Reduce non-patient traffic within the practice
Support persons |  | Ex.
Contractors ( maintenance) |  | Ex.
Pathology collection |  | Ex.
Pharmacy pick up of prescriptions etc. |  | Ex.
All other non-patient visitors |  | Ex.
Triaging
Aim: Adapt your practice's triaging system to assume all symptomatic patients pose a possible risk of COVID-19 infection.
Adapt triage process to match current advice and practice position, consider: |  | Ex.
Triage resources for staff (updated) |  | Ex.
Triage of patients with cold/flu symptoms |  | Ex.
Triage of complex patients: Young children, the elderly, pregnant people, those difficult to assess via telehealth or those with difficulty in communication (updated) |  | Ex.
Handling patients that have physically arrived with epidemiology or symptoms (updated) |  | Ex.
What services are available in our region, including testing, after hours (new) |  | Ex.
Definitions for staff ( close contact, confirmed case) (updated) |  | Ex.
Triaging for COVID Positive patients (new) |  | Ex.
Personal Protective Equipment (PPE)
Aim: Have adequate PPE stores and know how and when it should be used for maximum efficiency.
Appropriate PPE usage dependent on risk (new) |  | Ex.
Stock |  | Ex.
Patient use and access (updated) |  | Ex.
Donning and Doffing (updated) |  | Ex.
Recording of fit test results |  | Ex.
Laundry and Uniform
Aim: Employ strict laundering procedures after each shift.
Current uniform procedures (updated) |  | Ex.
At home laundering |  | Ex.
On-site laundering |  | Ex.
Practice layout changes /infection control
Aim: Protect patients and staff by utilising the right PPE and infection control measures in the practice .
Seating distance and capacity (updated) |  | Ex.
Practice entrance and exit (updated) |  | Ex.
Isolation room entry and exit patient flow |  | Ex.
Waiting room |  | Ex.
Addition of doffing and donning areas |  | Ex.
Protection of staff , physical barriers, PPE |  | Ex.
Practice Cleaning |  | Ex.
Information to contract cleaners |  | Ex.
Clinic scheduling |  | Ex.
Clean air/ ventilation considerations (new) |  | Ex.
Isolation room/space utilisation
Aim: Create a designated isolation room/area to separate patients with COVID-19 symptoms from the general waiting room if unable to see patients remotely.
Create a space/room/clinic time designated for seeing infectious patients or with current epidemiology |  | Ex.
Training on use of the isolation room and cleaning |  | Ex.
Cleaning schedules and responsibilities |  | Ex.
Isolation room/area - greeting, check in |  | Ex.
Isolation room/area - greeting, check out |  | Ex.
Telehealth
Aim: Predominantly use Telehealth in your practice for greeting, treating and checking out patients remotely.
Enable Telehealth via phone/video call |  | Ex.
Use of Telehealth |  | Ex.
Non-Medicare covered patients (no Medicare card or not eligible for MBS items) |  | Ex.
E-prescribing and patient documentation
Aim: Enable methods to be able to remotely send prescriptions, pathology, referrals and patient documentation.
Patient documentation |  | Ex.
Prescriptions |  | Ex.
Messaging to other providers |  | Ex.
Utilise digital methods to send patient documentation |  | Ex.
Online booking and Website
Aim: Put processes in place to triage all patients booking on line for symptoms and epidemiology
Messaging and communication on your online platforms , and website |  | Ex.
Online booking preferences |  | Ex.
New software/systems |  | Ex.
Patient Communication
Aim: How are you going to communicate your changes effectively and enforce the changes
Hold music/message |  | Ex.
Receptionists' phone call script |  | Ex.
Communications and language (new) |  | Ex.
Communication and posters |  | Ex.
Effective Patient Communication ( updated) |  | Ex.
Practice social media |  | Ex.
Covid Care at Home promotion ( new) |  | Ex.
Clinical Services
Aim: Temporarily restrict or redirect non-essential services as much as possible as the practice tightens its pandemic response.
Aerosol Producing procedures |  | Ex.
Home/external visits (updated) |  | Ex.
Existing non-essential services (updated) |  | Ex.
High risk/vulnerable patients |  | Ex.
Essential services |  | Ex.
COVID-19 vaccination clinic |  | Ex.
COVID-19 Assessment and Management |  | Ex.
Adopting the COVID Care at Home Program (new) |  | Ex.
Aged Care / Hospital Visits (new) |  | Ex.
Administration/Non-clinical
Aim: Put working-from-home plan into action where possible
Daily, weekly and monthly list of duties and responsibility for the team |  | Ex.
Software |  | Ex.
Online workflow |  | Ex.
Human Resources (HR)
Aim: Adapt to working from home models where practical
Working from home audit |  | Ex.
Working from home/external premises protocol |  | Ex.
Infection control training recent and up to date |  | Ex.
Staff training on PPE |  | Ex.
Staff screening |  | Ex.
Support |  | Ex.
Virtual socialisation |  | Ex.
Roster planning |  | Ex.
Online workflow |  | Ex.
Management of an positive case in a team member - Create an outbreak management plan (new) |  | Ex.
Management of close contact in a team member - Create an outbreak management plan (new) |  | Ex.
Furlough advice for Healthcare workers (new) |  | Ex.
Management of a postive case within the workplace (new) |  | Ex.
IT and phones systems
Aim: To adapt existing IT and phone systems for remote work with minimal business disruptions.
IT |  | Ex.
Phone lines |  | Ex.
Software |  | Ex.
Communication and responsibilities
Aim: Assign responsibilities for communicating changes and updates to the team
Role/s responsible for communicating the changes to the practice |  | Ex.
Role/s responsible for keeping abreast of changes in the COVID-19 pandemic |  | Ex.
Role/s responsible for agreeing to escalate or deescalate the stages |  | Ex.
Staff meetings |  | Ex.
GP Urgent Care Practices
Aim: Consider plans to keep services open for GP Urgent Care patients, taking into account increased demand due to the situation.
GP Urgent Care appointments |  | Ex.
Other
Aim: Use this space for anything else relevant to your practice that hasn't already been covered above.

## Stage 3 - Living with COVID-19
Pandemic Response Plan Stage 3 - Living with COVID-19
This stage captures COVID-19 widespread in the community and a new normal of living with COVID-19 in the community based on direction from the WA Department of Health. This scenario is high prevalence and medium risk incorporating a hybrid practice model.
Consider what would be a trigger for your practice to implement this Stage 3? Plan and write it in the blank space below - select the space below to see an example.
(Consider using SMART (Specific, Measurable, Achievable, Realistic, and Timely) to define)
Click in this box for suggestions
Practice Operations | Adaptions to Operations for Stage 3
You can add or remove these operations depending on the relevancy to your practice. Please click on each operation to be taken to the appropriate resources. | What operations will your practice change to adapt? Try to be explicit. Some items may require a separate procedure document to detail the changes. Select the cells on the right with "Ex." for an example.
Patient Journey/Flow Changes
Aim: Sustainable screening for COVID-19 prior to entrance, adapting patient journey and work flows to reduce the risk of transmission while restoring face-to-face services.
Screening of patients |  | Ex.
Greeting and screening questions |  | Ex.
Entrance/Front Desk |  | Ex.
PPE use for patients and greeting staff |  | Ex.
Check in process |  | Ex.
Non-patient Traffic
Aim: Reduce potential transmission by limiting access to the practice to only essential patient and people traffic.
Support persons |  | Ex.
Contractors ( maintenance) |  | Ex.
Pathology collection |  | Ex.
Pharmacy pick up of prescriptions etc. |  | Ex.
All other non-patient visitors |  | Ex.
Triaging
Aim: To adapt your practice's triaging process based on the latest clinical and testing advice. Including the use of Telehealth, isolation room, PPE.
Adapt triage process to match current advice and practice position, consider: |  | Ex.
Triage resources for staff (updated) |  | Ex.
Triage of patients with cold/flu symptoms |  | Ex.
Triage of complex patients: Young children, the elderly, pregnant people, those difficult to assess via telehealth or those with difficulty in communication (updated) |  | Ex.
Handling patients that have physically arrived with epidemiology or symptoms (updated) |  | Ex.
What services are available in our region, including testing, after hours (new) |  | Ex.
Definitions for staff ( close contact, confirmed case) (updated) |  | Ex.
Triaging for COVID Positive patients (new) |  | Ex.
Personal Protective Equipment (PPE)
Aim: Have adequate PPE stores and know how and when it should be used for maximum efficiency.
Appropriate PPE usage dependent on risk (new) |  | Ex.
Stock |  | Ex.
Patient use and access (updated) |  | Ex.
Donning and Doffing (updated) |  | Ex.
Establishing ongoing fit testing processes |  | Ex.
Laundry and Uniform
Aim: Establish what are going to be the uniform and laundering procedures on going
Current uniform procedures (updated) |  | Ex.
At home laundering |  | Ex.
On-site laundering |  | Ex.
Practice layout changes /infection control
Aim: Following public health guidance adjust the layout of the practice to reduce the potential of infection as far as reasonably possible.
Seating distance and capacity (updated) |  | Ex.
Practice entrance and exit (updated) |  | Ex.
Isolation room entry and exit patient flow |  | Ex.
Waiting room |  | Ex.
Addition of doffing and donning areas |  | Ex.
Protection of staff , physical barriers, PPE |  | Ex.
Practice Cleaning |  | Ex.
Information to contract cleaners |  | Ex.
Clinic scheduling |  | Ex.
Clean air/ ventilation considerations (new) |  | Ex.
Isolation room/space utilisation
Aim: Review the use of designated isolation room/area to see potentially infection patients or vulnerable/difficult patients/children etc
Create a space/room/clinic time designated for seeing infectious patients with current epidemiology |  | Ex.
Training on use of the isolation room and cleaning |  | Ex.
Cleaning schedules and responsibilities |  | Ex.
Isolation room/area - greeting, check in |  | Ex.
Isolation room/area - greeting, check out |  | Ex.
Telehealth
Aim: Continue the use of Telehealth in your practice for greeting, treating and checking out patients remotely to minimise infection
Enable Telehealth via phone/video call |  | Ex.
Use of Telehealth |  | Ex.
Non-Medicare covered patients (no Medicare card or not eligible for MBS items) |  | Ex.
E-prescribing and patient documentation
Aim: Continue to embed and refine methods to be able to remotely send prescriptions, pathology, referrals and patient documentation.
Patient documentation |  | Ex.
Prescriptions |  | Ex.
Messaging to other providers |  | Ex.
Utilise digital methods to send patient documentation |  | Ex.
Online booking and Website
Aim: How are you going to use your online booking system to support your new model of care
Messaging and communication on your online platforms , and website |  | Ex.
Online booking preferences |  | Ex.
New software/systems |  | Ex.
Patient Communication
Aim: How are you going to communicate your changes effectively and enforce the changes
Hold music/message |  | Ex.
Receptionists' phone call script |  | Ex.
Communications and language (new) |  | Ex.
Communication and posters |  | Ex.
Effective Patient Communication ( updated) |  | Ex.
Practice social media |  | Ex.
Covid Care at Home promotion (new) |  | Ex.
Clinical Services
Aim: Reflect on all services provided, following public health guidelines, establish plans to be able to safely perform all usual medical services
Aerosol Producing procedures |  | Ex.
Home/external visits (updated) |  | Ex.
Existing non-essential services (updated) |  | Ex.
High risk/vulnerable patients |  | Ex.
Essential services |  | Ex.
COVID-19 vaccination clinic |  | Ex.
COVID-19 Assessment and Management |  | Ex.
Adopting the COVID Care at Home Program (new) |  | Ex.
Care for post COVID-19 Patients |  | Ex.
Aged Care / Hospital Visits (new) |  | Ex.
Administration/Non-clinical
Aim: Make sustainable workflows to accommodate working from home for the non-clinical aspects of the practice.
Daily, weekly and monthly list of duties and responsibility for the team |  | Ex.
Software |  | Ex.
Online workflow |  | Ex.
Human Resources (HR)
Aim: Using State and Public Health guidance establish a flexible model of work that focuses on safety as well as sustainable access to work
Working from home audit |  | Ex.
Working from home/external premises protocol |  | Ex.
Infection control training recent and up to date |  | Ex.
Staff training on PPE |  | Ex.
Staff screening |  | Ex.
Support |  | Ex.
Virtual socialisation |  | Ex.
Roster planning |  | Ex.
Online workflow |  | Ex.
Management of an positive case in the team - Create an outbreak management plan (new) |  | Ex.
Management of close contact in a team member - Create an outbreak management plan (new) |  | Ex.
Furlough advice for Healthcare workers (new) |  | Ex.
Management of a postive case within the workplace (new) |  | Ex.
IT and phones systems
Aim: Reflect on the current system, what improvements can be made for remote work with minimal business disruptions.
IT |  | Ex.
Phone lines |  | Ex.
Software |  | Ex.
Communication and responsibilities
Aim: Continue to keep a high level of communications to the team, with a focus on how to reach a hybrid working team.
Role/s responsible for communicating the changes to the practice |  | Ex.
Role/s responsible for keeping abreast of changes in the COVID-19 pandemic |  | Ex.
Role/s responsible for agreeing to escalate or deescalate the stages |  | Ex.
GP Urgent Care Practices
Aim: Consider plans to keep services open for GP Urgent Care patients.
GP Urgent Care appointments |  | Ex.
Other
Aim: Use this space for anything else relevant to your practice that hasn't already been covered above.

## Practice Closure
Pandemic Response Plan - Practice Closure
This stage is designed for a situation where the practice is unable to stay open due to PPE unavailability, catastrophic HR deficit due to sickness or isolation or a public health enforced closure. In this scenario there is substantial confirmed community transmission and only telehealth consultations are viable from outside of the medical practice environment.
Consider what would be a trigger for your practice to implement this stage plan and write it in the blank space below - select the space below to see an example.
(Consider using SMART (Specific, Measurable, Achievable, Realistic, and Timely) to define)
Click in this box for suggestions
Practice Operations | Adaptions to Operations
You can add or remove these operations depending on the relevancy to your practice. Please click on each operation to be taken to the appropriate resources. | What operations will your practice change to adapt further to the prior stage? Try to be explicit. Some items may require a separate procedure document to detail the changes. Select the cells on the right with "Ex." for an example.
Patient Journey/Flow Changes
Aim: Create workflows and patient journey that are entirely via Telehealth or via an alternative service.
Screening of patients (updated) |  | Ex.
Greeting and screening questions |  | Ex.
Entrance/Front Desk |  | Ex.
Patients in need of a physical appointment |  | Ex.
Non-patient Traffic
Aim: Redirect services that previously required patients to physically attend the practice.
Support persons |  | Ex.
Contractors ( maintenance) |  | Ex.
Pathology collection |  | Ex.
Pharmacy pick up of prescriptions etc. |  | Ex.
All other non-patient visitors |  | Ex.
Triaging
Aim: Create a resource that guides staff with how to direct a patient under your new remote structure.
Adapt triage process to match current advice and practice position, consider: |  | Ex.
Triage resources for staff (updated) |  | Ex.
Triage of patients for alternative models of care (updated) |  | Ex.
What services are available in our region, including testing, after hours (new) |  | Ex.
Definitions for staff ( close contact, confirmed case) (updated) |  | Ex.
Triaging for COVID Positive patients (new) |  | Ex.
Personal Protective Equipment (PPE)
Aim: Have adequate PPE stores and know how and when it should be used optimally
Appropriate PPE usage dependent on risk (new) |  | Ex.
Stock |  | Ex.
Donning and Doffing (updated) |  | Ex.
Laundry and Uniform
Aim: Employ strict laundering procedures after each shift.
Current uniform procedures (updated) |  | Ex.
At home laundering |  | Ex.
On-site laundering |  | Ex.
Practice layout changes /infection control
Aim: Review the practice layout to fit with population health guidance. Practice is likely to be closed to public use, work with population health for a reopening plan.
Seating distance and capacity (updated) |  | Ex.
Practice entrance and exit (updated) |  | Ex.
Isolation room entry and exit patient flow |  | Ex.
Waiting room |  | Ex.
Addition of doffing and donning areas |  | Ex.
Protection of staff , physical barriers, PPE |  | Ex.
Practice Cleaning |  | Ex.
Information to contract cleaners |  | Ex.
Clinic scheduling |  | Ex.
Clean air/ ventilation considerations (new) |  | Ex.
Isolation room/space utilisation
Aim: Have the area terminal cleaned and ready for reopening
Create a space/room/clinic time designated for seeing infectious patients with current epidemiology |  | Ex.
Training on use of the isolation room and cleaning |  | Ex.
Cleaning schedules and responsibilities |  | Ex.
Isolation room/area - greeting, check in |  | Ex.
Isolation room/area - greeting, check out |  | Ex.
Telehealth
Aim: Predominantly use Telehealth in your practice for greeting, treating and checking- out patients remotely.
Enable Telehealth via phone/video call |  | Ex.
Use of Telehealth |  | Ex.
Non-Medicare covered patients (no Medicare card or not eligible for MBS items) |  | Ex.
E-prescribing and patient documentation
Aim: Enable methods to be able to remotely send prescriptions, pathology, referrals and patient documentation.
Patient documentation |  | Ex.
Prescriptions |  | Ex.
Messaging to other providers |  | Ex.
Utilise digital methods to send patient documentation |  | Ex.
Online booking and Website
Aim: To relay your practice changes on to your booking system
Messaging and communication on your online platforms , and website |  | Ex.
Online booking preferences |  | Ex.
Patient Communication
Aim: How are you going to communicate with your patients and keep them up to date regularly
Hold music/message |  | Ex.
Receptionists' phone call script |  | Ex.
Communications and language (new) |  | Ex.
Communication and posters |  | Ex.
Effective Patient Communication (updated) |  | Ex.
Practice social media |  | Ex.
Covid Care at Home promotion ( new) |  | Ex.
Clinical Services
Aim: To determine what services can be postponed, what can be done via Telehealth, what will need to be diverted to another health services provider or location. Communicate with your population health team to establish an alternative service plan.
Home/external visits (updated) |  | Ex.
Existing non-essential services (updated) |  | Ex.
High risk/vulnerable patients |  | Ex.
Essential services |  | Ex.
COVID-19 vaccination clinic |  | Ex.
COVID-19 Assessment and Management |  | Ex.
Adopting the COVID Care at Home Program (new) |  | Ex.
Aged Care / Hospital Visits (new) |  | Ex.
Administration/Non-clinical
Aim: Put working-from-home plan into action.
Daily, weekly and monthly list of duties and responsibility for the team |  | Ex.
Software |  | Ex.
Online workflow |  | Ex.
Human Resources (HR)
Aim: Support the team in a work-from-home model.
Working from home audit |  | Ex.
Working from home/external premises protocol |  | Ex.
Infection control training recent and up to date |  | Ex.
Staff training on PPE |  | Ex.
Staff screening |  | Ex.
Support |  | Ex.
Virtual socialisation |  | Ex.
Online workflow |  | Ex.
Management of an positive case in the team - Create an outbreak management plan (new) |  | Ex.
Management of close contact in a team member - Create an outbreak management plan (new) |  | Ex.
Furlough advice for Healthcare workers (new) |  | Ex.
Management of a postive case within the workplace (new) |  | Ex.
IT and phones systems
Aim: Refine the practice's plan for working from home to identify and minimise business disruptions.
IT |  | Ex.
Phone lines |  | Ex.
Software |  | Ex.
Communication and responsibilities
Aim: Assign responsibilities and accountabilities to communicate the changes and updates to the team in a remote work model
Role/s responsible for communicating the changes to the practice |  | Ex.
Role/s responsible for keeping abreast of changes in the COVID-19 pandemic |  | Ex.
Role/s responsible for agreeing to escalate or deescalate the stages |  | Ex.
Staff meetings |  | Ex.
GP Urgent Care Practices
Aim: Establish plans with alternative services in case of lock out for GP Urgent care patients.
GP Urgent Care appointments |  | Ex.
Other
Aim: Use this space for anything else relevant to your practice that hasn't already been covered above.

## Resources
Resource Collection
Resources for COVID-19 updates to develop screening protocols
WA Department of Health: Clinician Alerts
WA Department of Health: Testing Directions
WA Department of Health: SHICC /PHEOC Bulletins
Department of Health: Coronavirus Disease 2019 (COVID-19) SoNG CDNA National Guidelines for Public Health Units
WA Department of Health - Transition Policies and resources for healthcare workers (NEW)
Health Pathways -COVID-19 Self - Care Patient Triage and Support (NEW)
Resources for Healthcare facility infection prevention / practice layout/ patient flow/ patient and non patient traffic
WA Department of Health: COVID-19 Infection Prevention and Control in Western Australian Healthcare Facilities - Infection prevention and control and PPE section | WA Department of Health -Information on COVID-19 and building ventilation (NEW)
Practice Assist - Living with COVID-19 checklist and toolkit | Oz Sage - Safe Indoor Air (ventilation) - article and PDF (NEW)
Health Pathways -COVID-19 PPE,Infection Control and Exposure Response - General Infection control requirements (updated) | Department of Health Minimising the risk of COVID-19 transmission in a primary health care setting (NEW)
RACGP: Managing patients who present with respiratory symptoms in the context of COVID-19
WA Department of Health: High risk Exposure in a workplace and furloughing of healthcare workers (updated)
Department of Health: COVID 19 Environmental Cleaning and disinfection principles for health and residential care facilities
RACGP Principles of Infection Control
Australian Commission on Safety and Quality In Health Care - Environmental Cleaning: Information for Cleaners
Resources for Triage
Practice Assist- How do I respond to a COVID-19 positive patient? (NEW)
Practice Assist - Living with COVID-19 checklist and toolkit
RACGP: Managing patients who present with respiratory symptoms in the context of COVID-19
RACGP: Managing mild COVID-19 at home with assistance from your GP
RACGP: Patient resource - managing post-COVID-19 symptoms
Health Direct COVID -19 restriction tracker
Health Pathways - COVID-19 Assessment and Management
Health Pathways - COVID -19 Self - Care Patient Triage and Support (NEW)
Resources for Personal Protective Equipment (PPE)
Department of Health: Infection Control Expert Group - Guidance on the use of personal protective equipment (PPE) for health care workers in the context of COVID-19 | Resp- Fit - Fit Testing -Find a fit tester (NEW)
Department of Health: Personal protective equipment (PPE) for the health workforce during COVID-19 - General advise on who should use it, the National Medical Stockpile
WA Department of Health - System Alert and Response - (PDF - PPE guidance) (NEW)
RACGP: Optimising use of PPE
Managing pandemic influenza in general practice: A guide for prevention, preparation, response and recovery.
WA Department of Health: COVID-19 Infection Prevention and Control in Western Australian Healthcare Facilities - Infection prevention and control and PPE section
Australian Nursing & Midwifery Federation: COVID-19 Laundering of Healthcare Worker Uniforms Evidence Brief
Health Pathways -COVID-19 PPE, Infection Control and Exposure Response (NEW)
WA Department of Health - Don and Doffing information posters (updated)
WAPHA - Practice Assist - COVID -19 FAQ National Medical Stockpile
National COVID-19 Clinical Evidence Taskforce - Eye Protection practice points
Resources for Isolation room/space
Practice Assist - Living with COVID-19 checklist and toolkit
WA Department of Health: COVID-19 Infection Prevention and Control in Western Australian Healthcare Facilities - Infection prevention and control and PPE section
Health Pathways -COVID-19 PPE, Infection Control and Exposure Response (NEW)
Resources for Telehealth
WA Primary Health Alliance: Practice Assist - Becoming Telehealth Enabled Fact Sheet
WA Primary Health Alliance: Practice Assist - Becoming Telehealth Enabled Checklist
Department of Health: COVID-19 Temporary MBS Telehealth Services ( updated)
WA Primary Heath Alliance: Practice Assist -Health Direct Video Call
HealthPathways- COVID-19 - Telehealth
Practice Assist - Digital Health Toolkit
Resources for E-prescribing and patient documentation
Australian Digital Health Alliance: Electronic prescribing for prescribers
Practice Assist - Digital Health Tool Kit - Secure Messaging
HealthPathways - COVID-19 - Electronic Prescribing
RACGP - Using email in General Practice
Office of the Australian Information Commissioner - Communications with patients
Resources for Online booking and Website
HealthPathways -COVID-19 Practice Management - Care Delivery ( contact your online provider for guidance specific to your medical practice)
Resources for Patient Communication
HealthPathways -COVID-19 Practice Management - Care Delivery - Screening | WA Government - COVID -19 Testing and Isolation Guide ( including posters) (NEW)
WA Department of Health Healthy WA- COVID-19 Resources
Trello Board collection of posters and resources for COVID - 19
Department of Health COVID -19 resources for general public
RACGP: Managing mild COVID-19 at home with assistance from your GP
RACGP: Patient resource - managing post-COVID-19 symptoms
WA department of health - Fact sheets and further resources - Patient Resources
Healthy WA - COVID -19 - Consumer information and resources (NEW)
Train IT Medical - CESPHN Webinar "challenging communication in challenging times"
Resources for Clinical Services
WA Department of Health: COVID-19 Infection Prevention and Control in Western Australian Healthcare Facilities - Infection prevention and control and PPE section | WAPHA -Caring for COVID-19 positive people in your region (NEW)
Practice Assist - Living with COVID-19 checklist and toolkit | WA department of health - Test, Trace. Isolate, Quarantine(TTIQ) plan including close contact and isolation definitons (NEW)
Department of Health: ATAGI statement on use of COVID-19 vaccines in an outbreak setting | COVID Care at home / RAT registration page (NEW)
Department of Health: ATAGI Guiding Principles for maintaining immunisation services during COVID-19 pandemic | Covid Care at home Patient Information (NEW)
HealthPathways -COVID-19 PPE, Infection Control, and Exposure Response (NEW) | HealthPathways - Residential Care Facilities (NEW)
HealthPathways -COVID-19 Impacts and Information (updated)
HealthPathways - COVID - 19 Impact on Clinical Care
Healthy WA - Testing Sites
Health Pathways - COVID-19 Assessment and Management
RACGP: Home- care guidelines for patients with COVID-19 and post COVID -19
Resources for Administration/Non-clinical
Practice Assist - Living with COVID-19 checklist and toolkit
RACGP - Using email in General Practice
Resources for Human Resources
GPRA: Working from home - advice for GP trainees during the COVID-19 pandemic | Practice Assist - COVID -19 Positive Case in your team - staff questionaire (NEW)
Department of Health: Work Permissions and Restrictions Framework for Workers in Health Care Settings Interim Guidance ( NEW) | WA government - Critical Worker Definition (NEW)
HeathPathways - COVID-19 PPE, Infection Control. And Exposure Response (NEW) | Government of WA Dept. Mines, Industry Regulations and Safety - Working from home resources (NEW)
Black Dog Institute: TEN - The Essential Network for Health Professionals | WA Department of health - Test, Trace. Isolate, Quarantine(TTIQ) plan including close contact and isolation definitons (NEW)
WA Department of Health: High risk Exposure in a workplace and furloughing of healthcare workers (updated) | WA Department of Health - Guidance for the management of COVID -19 in the workplace (NEW)
Australian Commission on Safety and Quality in Health Care - Infection Prevention and control E learning modules | WA Department of Health - Community Healthcare Practice Guidelines - COVID-19 guidelines for healthcare practices in the community for a high and very high case load environment (NEW)
Practice Assist - Living with COVID-19 checklist and toolkit - Section 4 (NEW)
Practice Assist - Close Contact in your practice team staff questionaire (NEW)
Resources for IT and phones systems
Health Pathways -COVID-19 Self - Care Patient Triage and Support (NEW) ( Contact your IT service provider, software vendor and communications provider for information relevant to your specific practice )
Resources for communication and responsibilities
HealthPathways - COVID-19 Self-Care Patient Triage and Support - Planning your emergency practice response (NEW)
Practice Assist - Living with COVID-19 checklist and toolkit
GP Urgent Care
WA Primary Health Alliance: GP Urgent Care
*Please note: These resources are relevant as of the 3rd March 2022 but may become outdated at the date of usage.
Please add any other resources that you find helpful to the blank spaces

## Glossary
Glossary
Term/ Acronym | Definition
AGP | Aerosol Generating Procedures - those procedures that promote the generation of fine airborne particles (aerosols) that may result in the risk of airborne transmission of disease.
AGB | Aerosol Generating Behaviours - behaviours that are more likely to generate higher concentrations of infectious respiratory aerosols such as persistent and/or severe coughing, screaming, shouting, and singing.
COVID -19 Symptoms | Symptoms are features that indicate a type of disease. For COVID-19 these are typically fever, sore throat, shortness of breath, dry cough, muscle aches and/or tiredness, loss of taste and smell, but can vary with variants
Critical Workers | Someone whose role cannot be undertaken at home and their role is critical to the COVID -19 response or key services.
Donning / Doffing | A term for the correct order of putting on ( Donning) and taking off (Doffing) PPE
Epidemiology | Is the word for the study of distribution and patterns of health and disease. In the COVID -19 context , the epidemiology criteria is what makes a person at a higher risk of infection. I.e. recent travel, their occupation, close contact, hotspot, WA Health Testing criteria bulletins keep up to date with Epidemiological criteria
Furlough | A term for forced leave of absence, can be paid or unpaid.
High Case Load | A term determined by and given by the WA state government that triggers specific WA state protocols for close contact definitions and testing and isolation
Infectious Period | The infectious period is generally considered to commence 48 hours prior to symptom onset, or positive test date if asymptomatic, until the time the COVID-19 case is cleared of infection or can cease isolation, as advised by Public Health or in accordance with the guideline for release from isolation
Isolation | Isolation is a term used for people who have the virus are and required to isolate from others to avoid spreading the virus.
PPE | Personal Protective Equipment - Recommended equipment to wear or use to protect against disease or foreign material
Quarantine | Quarantine is a term to describe someone who has been assessed as a higher risk of having COVID-19. Quarantine means you must remain in your home, hotel room or other accommodation for a set time established by the WA state government.
SAR | WA Health "System Alert and Response". A stepped alert system which determines levels of PPE, testing and tracing , and adjustments to the provision of health services
Screening | A series of questions or actions applied to all patients to quickly assess and separate out a patient group. I.e. Asking for symptoms, travel and contact history , taking temperature
SHICC | State Health Incident Coordination Centre - Dedicated emergency management response facility and the source of public health advise and bulletins
SoNG | Series of National Guidelines, developed between the Communicable Diseases Network Australia and endorsed by Australian Health Protection Principle Committee. National advise to public health units for notifiable diseases.
Triage | A system to determine the severity of a patient , and then how to direct that patient to the appropriate pathway or outcome.
TTIQ | Test,Trace, Isolate, Quarantine
Variants | A virus can mutate so that there are changes in how it behaves such as the impact on how easily spread it its ( contagiousness ) and its severity of disease it can cause ( virulence)
Very High Case Load | A term determined by and given by the WA state government that triggers specific WA state protocols for close contact definitions and testing and isolation specifically effecting critical workers
* please feel free to add your own items in the above blank spaces