| Step 1: PLAN What do you plan to do/achieve | By 30 September 2026 (three months), the practice will identify and recall eligible adult patients (≥18 years with risk conditions, Aboriginal and Torres Strait Islander ≥25 years, and all adults ≥65 years) and vaccinate at least 10% of those patients with the new 21vPCV pneumococcal vaccine, regardless of previous pneumococcal vaccination history (as long as they are 12 months apart). Note: Information regarding the schedule changes located in additional information page |
| --- | --- |
| Step 2: DO Outline the steps you will undertake | Brief Summary of steps - Generate patient lists using extraction tool - Validate eligibility with clinical team - Send recalls (SMS/calls) - Offer vaccination opportunistically during consultations - Document vaccinations in clinical software and AIR |
|  | Comprehensive steps Educate / Inform team of changes - Educate all staff on QI intent, goals, and expected outcomes - Educate clinical staff on new pneumococcal schedule: - ensure all clinical staff are aware of where to find up to date Australian Immunisation Handbook - NCIRS – has evidenced based info & FAQ sheets - If required, train staff to: - Run queries (SQL/clinical search tools) - Use recall and reminder systems effectively - Train staff to offer vaccine opportunistically. Highlight key times to consider such as a care plan review, health assessment, when this patient attends for another vaccination or even when accompanying family members to an appointment. - Consider if additional staffing or dedicated clinics are required: - Nurse-led vaccination sessions - Increased admin support for recalls Identifying data - Collect starting data by running clinical system search (Best Practice query in ‘Other Information’ section): - Patients eligible for pneumococcal vaccination - Within this group, identify patients previously vaccinated (Prevenar and/or Pneumovax) and patients NOT previously vaccinated. - Document numbers into PDSA. - Review size of eligible patients needing to be contacted and consider: - If small number of patients - Is this a manageable list to be able to be recalled via phone? - If large number of patients: Is this number of patients too large to be doing a bulk SMS to? Does this need to be broken down into subgroups and sent at different intervals? (Suggested search queries for breaking down by age group in ‘Other Information’) - Export data into a usable recall list (either printing or bulk adding reminders) Implementing change - Implement any required documentation / template updates (example immunisation consent form or autofills) - Create recall template (SMS/ letter template, or phone script) - Order: Pneumococcal vaccine stock (21vPCV - Capvaxive) & patient education materials (if available) Recalling patients - For those patients with previous vaccination – ensure it has been 12 months since their last immunisation. If it has been less than 12 months, add a reminder on patients file for when they are due. Remember to use the Australian Immunisation Register (AIR), rather than practice management software for this, as patients may have had the vaccine elsewhere. - If using SMS, commence SMS Cycle - If large number of patients: Is this number of patients too large to be doing bulk SMS to? Does this need to be broken down into subgroups and sent at different intervals? (consider staffing capacity for phone calls, appointment availability and stock) - If using phone calls: - Consider who id best suited to make the calls / has capacity too - Consider creating a script for reception/ staff member making phone call Contact patient and document outcome If no answer: - Document attempt in accessible notes - Send SMS follow-up If patient answers: - Clearly explain new schedule and that the patient Eligibility even if previously vaccinated - Book vaccination appointment - Document discussion in patient notes Monitoring during implementation - Run data report weekly to track progress, consider using run chart template available in ‘Other Information’ for a progression visual to share with the practice. - Continue monitoring weekly for at least three to six months, sharing progress with the practice team to create motivation. |
| Step 3: STUDY What did you observe? | Compare: - Total eligible patients vs number vaccinated - Uptake in previously vaccinated vs never vaccinated groups Review: - Recall effectiveness (SMS response vs phone calls) - Barriers (e.g. patient confusion about “already vaccinated”) and what has worked to address these - Time consumption: how much time did this take to recall the patients? |
| Step 4: ACT Will you adopt, adapt or abandon this change? | ✅ ADOPT (continue as is) Use this if the data shows good uptake and the process worked well. - Adopt the pneumococcal recall process as standard practice - Continue routine identification and recall of eligible patients monthly 🔄 ADAPT (modify and improve) Use this if there were gaps, low uptake, or workflow issues - Consider: Refine recall messaging to improve patient understanding (e.g. simplify wording, emphasise single-dose schedule) - Consider: Adjust recall methods based on effectiveness: - Increase phone recalls if SMS uptake is low - Use multiple contact attempts or mixed-method recalls ❌ ABANDON (stop or significantly change approach) - Abandon the current recall strategy if uptake remains low despite multiple attempts - Reassess practice capacity, staffing, and competing priorities before repeating the cycle |

………..

Changes to adult pneumococcal schedule 1 July 2026

Links - Adult pneumococcal vaccination – Program advice for health professionals - Pneumococcal vaccines – frequently asked questions (FAQs) ¦ NCIRS - National Immunisation Program – Program advice for consumers Key changes - In 2026, the NIP adult pneumococcal schedule will be updated. - The existing two pneumococcal vaccines, 13vPCV and 23vPPV, will be replaced with a single product. - Eligibility for select groups will be expanded to include younger ages. Details - From 1 July, 21vPCV Capvaxive® (MSD) will be free under the NIP for: - individuals with an at-risk condition aged ≥18 years - Aboriginal and Torres Strait Islander adults aged ≥25 years - All other adults aged ≥65 years - The new 21vPCV program, when combined with the 20vPCV paediatric program, will provide broader serotype coverage overall, and substantially simplify the schedule for providers Previous 2025 Immunisation schedules (now Superseded) (now Superseded) Side-by-side summary Feature; Current (2025); New (2026). Vaccines; 13vPCV + 23vPPV; 21vPCV only. Doses; 2–3 doses; 1 dose. Timing; Staged (12 months + 5 years); One-off. Eligibility - Aboriginal; ≥50 years; ≥25 years ✅ expanded. Eligibility - General; ≥70 years; ≥65 years ✅ expanded. Eligibility - At-risk adults; ≥18 years; ≥18 years.

| Any other information? Examples: notes, screenshots, graphs, context information, resources, Brainstorming |  |
| --- | --- |
| SQLS for Best Practice Knowledge base - Bp Premier Support Guidance - Database Search Category; SQL File. All eligible; All eligible and had either P13 P23 or P7. All eligible and NOT had either P13 P23 or P7. Individual categories; Aged over 18 and has MRC. Aged over 65. aged over 25 and ATSI. Category; SQL File. If have significant number of over 65+ Further age break; Aged 65 to 74. aged 75 to 84. aged 85 to 95. aged 95 over. Category; SQL File. want to target those with previous Pneumococcal vaccination history?; Aged over 18 and has MRC and had either P13 P23 or P7. Aged over 25 ATSI and had either P13 P23 or P7. Aged over 65 and had either P13 P23 or P7. Links Best Practice Knowledge base - Bp Premier Support Guidance - Database Search - Best Practice Knowledge base - Searching the Database - Best Practice Knowledge base - Supplied Database Queries - Useful Database Queries to Run |
| Any other information? Examples: notes, screenshots, graphs, context information, resources, Brainstorming |  |
| Run Chart template to track progress (This will automatically calculate the percentage and track this on the graph once the eligibility and vaccinated data is entered.) Also see our Clinician Assist WA » Immunisation – Adult page If you would like a Version of this PDSA Customised to be specific to your clinical software or practice workflows, please contact the QI Coaches at QI@wapha.org.au |  |
| Questions, Links and information: - What is a smart goal?: SMART Goals Cheat Sheet - How to document a PDSA? Guide to documenting a QI activity as a PDSA - Does this need to be documented in a PDSA or can it be captured in a QI log? Identifying and undertaking QI activities using PDSAs |  |

………..